## Slide 1: Project Delivery System

## Slide 2
PROJECT LIFE CYCLE
Phase 1- Pre-Construction
Phase 2- Design
Phase 3- Bidding and Procurement
Phase 4- Construction
Phase 5- Close Out

## Slide 3
Pre-Construction
Set Up Initial Engagement Meeting with Client
Review Site, Documents, Specifications and As Built Conditions
Prepare RFP for Design Services based on SOW, Budget & Schedule
Schedule Bid Meeting with Design Firms
Discuss Baseline Schedule and Cost Requirements
Organize Meeting with all Stakeholders to establish scope
Review RFP responses, evaluate and make recommendations to Client
Execute Design Contracts
Prepare SOW Document based upon input from all Stakeholders
Set Up Risk/Opportunity Register
Establish KPI’s
Utilize Best Practices
Set Up Change Management Log
Project Initiation
Distribute and Obtain Sign off that all parties agree with SOW
Establish Initial High-Level Baseline Schedule and Budget
Start
Scope Development
Establish Design RFP
Document Control
Design

## Slide 4
Design
Design Start (Design Programing)
Award Design Contract
Architect Initial Engagement
30% Design review Deliverable Checklist
Architect Fully Engaged in Design
Hold Design Kick Off Meeting
Establish Standards and Playbooks
MEP and IT Security Engineer Initial Engagement
Review Gap Analysis Results
Begin Long Lead Material Identification
30% Design Review (Schematic Design)
Coordinate Design Deliverables & Schedule for 30/60/90 & IFC
Document “As Is” As Built Conditions & Determine if Gap Study is Required
Provide Format for RFI’s and Submittals
Update Initial High-Level Schedule
Update Initial Budget ROM
Begin Value Engineering Review
Begin Constructability Review
Update Change Management and Risk/Opportunity Logs
Provide Fixed Architectural Design Layout (Frozen Layout)
60 %
Pre-Construction

## Slide 5
Design
60% Design Review (Design Development)
60% Design Review Deliverable/Checklist
Verify Code Compliance Review Completed (By Designers)
90% Design Review Deliverable Checklist
Update 60% Schedule
MEP and IT Security Engineering Fully Engaged in Design
Finalize Long Lead Material Identification
Update 60% ROM
Continue Value Engineering
Continue Constructability Review
90% Design Review (Construction Documents)
Order Long Leads if Required
Update 30% Schedule
Update 30% ROM
Update Change Management and Risk/Opportunity Logs
Verify Code Compliance with AHJ
Verify Design Drawing Coordination
Submit Permits
Continue Value Engineering Review
Continue Constructability Review
Update Change Management and Risk/Opportunity Logs
IFC
30%

## Slide 6
Design
IFC Design Review
IFC Design Review Deliverable Checklist
Update 90% Schedule
Update 90% ROM
Complete Value Engineering Review
Complete Constructability Review
Update Change Management and Risk/Opportunity Logs
Prepare Drawings To Go Out To Bid
Update Permit Schedule- Follow up on AHJ Review
90%
Bidding and Procurement

## Slide 7
Bidding and Procurement
Project Bidding
Establish Bidder Pre-Qualification Requirements
Prepare Bid Packets
Instructions to Bidders
Plans and Specifications
Design Standards
Baseline Schedule
Review Price Against Internal ROM
Receive and Evaluate Bids
Prepare Final Pricing Recommendations and Exclusions
Schedule Pre-Bid Meeting and Project Walk
Process and Review Bidder RFI’s
Bidding Phase VE and Constructability Review
Award Material and Vendor Subcontracts
Compare Bid Pricing
Review Bidder Qualifications and Exclusions
Construction
IFC

## Slide 8
Construction
Construction
Develop Final Baseline Construction Schedule
Prepare Final Cost Analysis
Establish Work Hours & Logistics
Review Schedule
Review Contract Documents
Review EHS
Review Project Scope
Project Mobilization
Update Baseline Schedule
Gather Permits if Available
Set Up Subcontractor Kick Off Meeting
Set Up Subcontractor Pull Plan Meeting
Update Risk/Opportunity and Change Logs
Update RFI & Submittal Logs
Monitor Material Delivery Against Need Dates
Hold Weekly O.A.C. Meetings
Perform Monthly Invoice Reviews
Ongoing Inspections and QA/QC
Substantial Completion
Begin Start Up & Commissioning
Final Inspections
Occupancy
Punchlist
Final Acceptance
Close Out
Bidding and Procurement

## Slide 9
Close Out
Project Closeout & Commissioning
END
Prepare Final Record Documents
Review Closeout Checklist
O&M’s
Final Accounting & Lien Waivers
As Built’ s
RFI &Submittal Logs
Warranties
Spare Parts
Punchlist Sign Off
Transmit Closeout Practice to Owner
Complete Commissioning
Construction